## START_HERE
START_HERE ¦ Dashboard ¦ Timeline_Tasks ¦ Vendor_Tracker ¦ Guest_RSVP ¦ Budget_Manager ¦ Decision_Notes
Wedding Control Board
Single source of truth for wedding planning progress, budget, vendors, guests, and decisions.
Workbook Map
Sheet | Layer | Purpose | User Action
SETUP_Dictionary | Config | Dropdown values and category mapping | Edit lists only when business rules change
Dashboard | Presentation | Executive control board | Review weekly; replace gray placeholders with native charts if desired
Timeline_Tasks | Data | Milestones and task ownership | Add or update tasks
Vendor_Tracker | Data | Vendor contracts and payment status | Add vendor contracts and payment status
Guest_RSVP | Data | Guest list and attendance counts | Track RSVP and table assignment
Budget_Manager | Data/Calc | Budget plan with vendor-based actuals | Enter planned budgets; formulas calculate actuals
Decision_Notes | Data | Decision log linked to tasks/vendors | Record calls, meetings, and verbal commitments
CALC_Summary | Calculation | Central calculation layer for dashboard formulas | Hidden/locked calculation area
Version | 1.0
Generated On | 2026-06-17
Post-Generation Checklist
1. Open the workbook in Microsoft Excel and use Data > Refresh All after adding new rows.
2. Replace gray dashboard placeholders with native Excel charts only if interactive chart objects are required.
3. Keep all source data inside the structured Excel tables; paste new rows directly below each table.
4. Use SETUP_Dictionary to extend dropdown categories instead of hardcoding new options.
5. Review Dashboard every week and update overdue tasks, vendor balances, and RSVP status.
Note on B24: All workbook content is English by request. The source specification was Chinese, translated into English field labels and values.

## SETUP_Dictionary
START_HERE ¦ Dashboard ¦ Timeline_Tasks ¦ Vendor_Tracker ¦ Guest_RSVP ¦ Budget_Manager ¦ Decision_Notes
Setup Dictionary
Task_Category | Task_Status | Owner | Vendor_Category | Pay_Status | Yes_No | Guest_Side | Guest_Group | RSVP_Status | Budget_Category | Note_Scenario | Link_Module
Venue & Ceremony | Not Started | Groom | Wedding Planning | Unpaid | Yes | Groom Side | Close Family | Confirmed | Venue & Banquet | Planner Call | Task
Core Vendors | In Progress | Bride | Host / MC | Deposit Paid | No | Bride Side | Close Friends | Declined | Core Vendor Services | Family Meeting | Vendor
Attire & Jewelry | Pending Confirmation | Joint | Makeup / Styling | Paid in Full |  | Mutual Friends | Classmates | Tentative | Attire & Jewelry | Site Visit | None
Paper & Gifts | Completed | Best Man | Photo / Video |  |  |  | Colleagues | Not Contacted | Paper & Gifts | WeChat Confirmation
Guest Execution |  | Maid of Honor | Banquet Venue |  |  |  | Other |  | Contingency / Misc | Inspiration Note
Other |  | Planning Team | Floral Design
Other
Vendor_Category | Budget_Category
Wedding Planning | Core Vendor Services
Host / MC | Core Vendor Services
Makeup / Styling | Core Vendor Services
Photo / Video | Core Vendor Services
Banquet Venue | Venue & Banquet
Floral Design | Venue & Banquet
Other | Contingency / Misc

## Dashboard
START_HERE ¦ Dashboard ¦ Timeline_Tasks ¦ Vendor_Tracker ¦ Guest_RSVP ¦ Budget_Manager ¦ Decision_Notes
Wedding Control Board
Last updated: | 2026-06-17
Completion Rate |  |  | Total Budget |  | Actual Cost |  |  | Confirmed Guests |  |  | Overdue Tasks
25% |  |  | 450000 |  | 260000 |  |  | 2 |  |  | 1
Open Planning Snapshot |  |  |  | Row Labels | Sum of Plan_Budget | Sum of Actual_Cost | [5 empty] | Row Labels | Sum of Est_Guests
Area | Current Value | Source |  | Attire & Jewelry | 60000 | 0 | [5 empty] | Confirmed | 2
Task completion | 25% | Timeline_Tasks |  | Contingency / Misc | 35000 | 0 | [5 empty] | Declined | 2
Budget used | 57.78% | Budget_Manager + Vendor_Tracker |  | Core Vendor Services | 110000 | 52000 | [5 empty] | Not Contacted | 1
Deposit paid | 65000 | Vendor_Tracker |  | Paper & Gifts | 25000 | 0 | [5 empty] | Tentative | 1
Final balance | 195000 | Vendor_Tracker |  | Venue & Banquet | 220000 | 208000 | [5 empty] | (blank)
Invited guests | 6 | Guest_RSVP |  | (blank) |  | 0 | [5 empty] | Grand Total | 6
Tentative guests | 1 | Guest_RSVP |  | Grand Total | 450000 | 260000
Upcoming Task Feed
Task_ID | Category | Task_Name | Due_Date
T003 | Guest Execution | Send first RSVP message to family groups | 2026-06-14
T001 | Venue & Ceremony | Confirm banquet venue and ceremony flow | 2026-06-24
T002 | Core Vendors | Book makeup artist and trial session | 2026-07-01
Task Workload
[5 empty] | Completed | In Progress | Not Started | Pending Confirmation | (blank) | Grand Total
|  |  |  | Bride |  |  |  | 1 |  | 1
|  |  |  | Groom | 1 |  |  |  |  | 1
|  |  |  | Joint |  | 1 |  |  |  | 1
|  |  |  | Planning Team |  |  | 1 |  |  | 1
(blank)
|  |  |  | Grand Total | 1 | 1 | 1 | 1 |  | 4

## Timeline_Tasks
START_HERE ¦ Dashboard ¦ Timeline_Tasks ¦ Vendor_Tracker ¦ Guest_RSVP ¦ Budget_Manager ¦ Decision_Notes
Timeline and Task Tracker
Task_ID | Category | Task_Name | Due_Date | Status | Owner | Notes
T001 | Venue & Ceremony | Confirm banquet venue and ceremony flow | 2026-06-24 | In Progress | Joint | Confirm ceremony start time and menu package
T002 | Core Vendors | Book makeup artist and trial session | 2026-07-01 | Pending Confirmation | Bride | Ask for trial makeup photos and schedule
T003 | Guest Execution | Send first RSVP message to family groups | 2026-06-14 | Not Started | Planning Team | Overdue sample to test warning rule
T004 | Paper & Gifts | Approve invitation wording and print quantity | 2026-07-08 | Completed | Groom | Final proof approved

## Vendor_Tracker
START_HERE ¦ Dashboard ¦ Timeline_Tasks ¦ Vendor_Tracker ¦ Guest_RSVP ¦ Budget_Manager ¦ Decision_Notes
Vendor and Payment Tracker
Vendor_ID | Category | Vendor_Name | Contact | Contract_Amt | Deposit_Paid | Final_Balance | Pay_Status | Contract_Saved
V001 | Banquet Venue | Harbor View Banquet Hall | Ms. Chen - 13800000000 | 180000 | 50000 | 130000 | Deposit Paid | Yes
V002 | Photo / Video | Blue Frame Studio | Mr. Lin - 13900000000 | 52000 | 15000 | 37000 | Deposit Paid | Yes
V003 | Floral Design | Mori Floral | Ivy - 13700000000 | 28000 | 0 | 28000 | Unpaid | No

## Guest_RSVP
START_HERE ¦ Dashboard ¦ Timeline_Tasks ¦ Vendor_Tracker ¦ Guest_RSVP ¦ Budget_Manager ¦ Decision_Notes
Guest List and RSVP Tracker
Guest_ID | Guest_Name | Side | Group | RSVP_Status | Est_Guests | Act_Guests | Table_No | Dietary_Req
G001 | Alex Zhang | Groom Side | Close Family | Confirmed | 2 | 2 | 1 | No alcohol
G002 | Mia Wang | Bride Side | Close Friends | Tentative | 1 | 0 |  | Vegetarian
G003 | Chris Lee | Mutual Friends | Colleagues | Not Contacted | 1 | 0
G004 | Emma Chen | Bride Side | Close Family | Declined | 2 | 0

## Budget_Manager
START_HERE ¦ Dashboard ¦ Timeline_Tasks ¦ Vendor_Tracker ¦ Guest_RSVP ¦ Budget_Manager ¦ Decision_Notes
Budget Manager
Budget_ID | Category | Plan_Budget | Actual_Cost | Variance | Status
B01 | Venue & Banquet | 220000 | 208000 | 12000 | ON TRACK
B02 | Core Vendor Services | 110000 | 52000 | 58000 | ON TRACK
B03 | Attire & Jewelry | 60000 | 0 | 60000 | ON TRACK
B04 | Paper & Gifts | 25000 | 0 | 25000 | ON TRACK
B05 | Contingency / Misc | 35000 | 0 | 35000 | ON TRACK

## Decision_Notes
START_HERE ¦ Dashboard ¦ Timeline_Tasks ¦ Vendor_Tracker ¦ Guest_RSVP ¦ Budget_Manager ¦ Decision_Notes
Decision Notes and Call Log
Note_ID | Date | Scenario | Content | Decision | Link_Module | Link_ID
N001 | 2026-06-17 | Planner Call | Confirmed trial makeup schedule with planner. | Trial makeup is booked for next Saturday at noon. | Task | T002
N002 | 2026-06-16 | Family Meeting | Discussed banquet table count assumptions. | Use 18 tables as initial planning baseline. | Vendor | V001

## CALC_Summary (hidden)
START_HERE ¦ Dashboard ¦ Timeline_Tasks ¦ Vendor_Tracker ¦ Guest_RSVP ¦ Budget_Manager ¦ Decision_Notes
Calculation Summary
Metric | Formula / Value
Total Tasks | 4
Completed Tasks | 1
Completion Rate | #VALUE!
Overdue Tasks | 1
Total Budget | 450000
Actual Cost | 260000
Deposit Paid | 65000
Final Balance | 195000
Invited Guests | 6
Confirmed Guests | 2
Tentative Guests | 1
Upcoming Tasks